## Sheet1
Finding | Observation | Current Status
F#1 – Broken Authentication | Direct access to Menu.aspx allows bypassing the login page. | Fixed in UAT – Pending GIS validation.
F#2 – Sitewide Broken Authorization (Throttle) | Unauthorized users can access pages/functions by navigating directly to URLs and throttling the network connection. | Fixed in UAT for WF_ApplicationDataEntry.aspx and WF_CA.aspx. Pending GIS benchmarking. Once validated, the fix will be extended across the site.
F#4 – Storage of Password in a Reversible Format | Username/password and other sensitive credentials are stored in a reversible/Base64 format. | Implementation in progress – Strong cryptographic encryption is being implemented.
F#5 – Sitewide SQL Injection | Multiple fields across the application are vulnerable to SQL injection involving both Oracle and MSSQL connections. | Partially implemented. Fix completed for a few pages. Remaining pages are in progress. This is an extensive sitewide activity and requires significant implementation effort.
F#7 – Sitewide Improper Data Validation | Request parameters can be modified; sensitive information can be exposed; read-only records can potentially be modified and submitted to the database. | Solution under discussion/finalization. Sitewide implementation is extensive and will require significant effort.
F#8 – Unauthenticated Services | Generated PDF files have predictable filenames, and URLs can potentially be reused from another browser/user. | Solution under discussion/finalization. Sitewide implementation is extensive and will require significant effort.
F#9 – Unauthorized User Can View Staff Salary | Unauthorized users can access sensitive salary information. | Implementation in progress.
F#14 – Potential Directory Traversal Attack | Potential directory traversal vulnerability identified. | Analysis in progress.