## Overview
Project Status Tracker
Dynamic overview driven by the Project Tracker sheet.
Unique JIRA IDs 26 |  | Production Issues 4
Status Count
Status | Count
Development | 5
SIT | 0
UAT | 1
EA | 0
In Progress | 2
RTB - Handover | 5
Grooming | 2
Pending | 2
Staging | 0
FSD | 1
Gone Live | 5
Go-Live | 1
PGL | 0
Analysis | 0
Support | 2

## Project Tracker
Sno | JIRA ID | Initiative / Title | Status | Developer | Grooming | FSD | EA | Dev | SIT | UAT | Staging | Go-Live | RTB - Handover
1 | DMGT-22 | ESG Millionaire Draw / ESG Millionaire ECD | Gone Live |  | ü | ü | ü | ü | ü | ü | ü | ü | û
2 | DMGT-65 | HF48 - Phase 1 | Gone Live | Manish | ü | ü | ü | ü | ü | ü | ü | ü | û
3 | DMGT-253 | HF-Product Takaful Provider Integration and Rate Management | Grooming |  | ü
4 | DMGT-328 | Addition and Deletion Customer Details in HFLMS | In Progress |  | ü
5 | DMGT-407 | Dated Security Cheque Printing (HFLMS & FinnOne) | Pending |  | ü
6 | DMGT-442 | HF Emirates Face Recognition (EFR) - Phase 1 | Go-Live |  | ü
7 | DMGT-443 | DDA Cancellation | UAT |  | ü
8 | DMGT-698 | Migration of DIB Legacy to HFLMS | Support |  | – | – | ü | ü | û
9 | DMGT-947 | Addition of customer name fields(Arabic) HF LMS | Development | Sneha | ü
10 | DMGT-1020 | Dedup Logic Controls in DIB Customer Onboarding Platforms | Development |  | ü
11 | DMGT-1260 | ESD - Climate Risk Data | Gone Live |  | ü
12 | DMGT-1272 | Input Fields Validation / Input fields validations | In Progress |  | ü
13 | DMGT-1340 | AECB for Sales | Gone Live |  | ü
14 | DMGT-1406 | CPR Personal Data Consent Management | Grooming |  | û | û | û | û | û | û | û | û | û
15 | DMGT-1416 | MBRE Non Subsidy | RTB - Handover |  | ü
16 | DMGT-1525 | EMX Delivery Partner | Support |  | ü
17 | DMGT-1526 | QR code Liability and Non-Liability Letter | Gone Live | Hariprasath | ü |  | ü | ü | ü | ü | ü | ü | ü
18 | DMGT-1792 | Digitization of HF contract documents and contract mapping | Development | Raquib
19 | DMGT-1825 | CRAT PGL Issue - LAST REVIEW DATE not passed to CRAT | Pending
20 | DMGT-1842 | EFR billing | FSD
21 | DMGT-1943 | HF48 Phase 2 | Development
22 | DMGT-1966 | Duplicate CIF Linkage of closed customer | Development
23 | DMGT-1981 | Low Doc / Create a flag in HF LMS to identify the low doc customers | RTB - Handover |  | ü | ü | ü | ü | ü | ü | ü | ü | û
24 | DMGT-2046 | DR Module | RTB - Handover |  | ü | ü | ü | ü | ü | ü | ü | ü | û
25 | DMGT-2135 | Frontline hero offer HF / Frontliner Hero | RTB - Handover |  | ü | ü | ü | ü | ü | ü | ü | ü | û
26 | DMGT-341 | CIF data enhancements | RTB - Handover |  | ü | ü | ü | ü | ü | ü | ü | ü | û

## Production Issues
JIRA ID | Initiative | Grooming | FSD Sent | FSD Sign off | EA | Dev | SIT | UAT | Staging | Go-Live | PGL | RTB - Handover | Status | Remarks | Delay Remarks | Developer
NA | PDF WITH ZERO KB in DDS UAT TEST - DDS Production issue
NA | Payment Flag in the MRC Report - Production issue
NA | MF202826 - ANTOINE HADDAD - MF147986 - Production issue
NA | Aftersales Performance Improvement