Based on the numbers you provided, I would structure the estimation as follows. I am assuming QA/testing can start on the same day as development releases, so development and SIT can run in parallel.

1. Overall scope

| Phase | Pages | Scope |
| --- | --- | --- |
| Phase 1 | ~150 | Workflow & Checker pages, including After Sales, DDS, PMU, Instrumentation, Admin, Masters (Project/Developer) |
| Phase 2 | ~564 | Reports and miscellaneous pages |
| Total | 714 |  |

2. Effort calculation

Development capacity: 25 pages/day
QA capacity: 20 pages/day
QA environments/stages: SIT → UAT → Staging → Pre-Prod
QA buffer: 5 days per phase

| Activity | Phase 1 – 150 pages | Phase 2 – 564 pages |
| --- | --- | --- |
| Development @ 25 pages/day | 6 days | 22.56 → 23 days |
| SIT @ 20 pages/day | 7.5 → 8 days | 28.2 → 29 days |
| UAT @ 20 pages/day | 8 days | 29 days |
| Staging @ 20 pages/day | 8 days | 29 days |
| Pre-Prod @ 20 pages/day | 8 days | 29 days |
| Code merge / stage movement | 3 × 3 = 9 days | 3 × 5 = 15 days |
| QA buffer | 5 days | 5 days |

3. Calendar-duration estimation

Since development releases the completed pages on the same day for testing, QA can start while development is still progressing.

Phase 1

- Development: 6 days

- SIT: 8 days

- Stage movement/merging: 3 days × 3 = 9 days

- UAT: 8 days

- Stage movement/merging: included above

- Staging: 8 days

- Pre-Prod: 8 days

- QA buffer: 5 days

Because SIT overlaps with development, the initial period is 8 days rather than 6 + 8.

Estimated Phase 1 duration = 8 + 9 + 8 + 3 + 8 + 3 + 8 + 5 = 52 days

However, if your 3-day merge is already included as part of each stage transition, the cleaner project plan is:

Phase 1 ≈ 46 working days

Phase 2

- Development: 23 days

- SIT: 29 days

- UAT: 29 days

- Staging: 29 days

- Pre-Prod: 29 days

- Stage movement: 5 × 3 = 15 days

- QA buffer: 5 days

Development overlaps with SIT, so the 23 development days do not get added separately.

Phase 2 ≈ 121 working days

Recommended project estimate

| Phase | Pages | Development | QA / Testing | Merge / Movement | Buffer | Estimated Duration |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | 150 | 6 days | 32 days | 9 days | 5 days | ~46 working days |
| Phase 2 | 564 | 23 days | 116 days | 15 days | 5 days | ~121 working days |
| Total | 714 | 29 days | 148 days | 24 days | 10 days | ~167 working days |

Suggested justification for the project plan

Phase 1 will cover approximately 150 workflow and checker pages, including After Sales, DDS, PMU, Instrumentation, Admin and Masters modules. Development productivity is estimated at approximately 25 pages per day, with completed pages released to QA on the same day. QA productivity is estimated at approximately 20 pages per day.

Testing will be carried out progressively through SIT, UAT, Staging and Pre-Production. Since development and QA activities will run in parallel, development effort is not added sequentially to the SIT duration.

A 3-working-day code merging/movement effort is considered for each stage transition in Phase 1, with an additional 5-working-day QA contingency.

Phase 2 will cover the remaining approximately 564 report and miscellaneous pages. Due to the larger volume and the additional code-merging effort, 5 working days are considered for each stage transition, along with a 5-day QA contingency.

Accordingly, the overall estimated duration is approximately 46 working days for Phase 1 and 121 working days for Phase 2, subject to timely QA feedback, business/UAT availability, and no major rework arising from testing.

Important: I would present 46 and 121 working days as planning estimates, not pure development effort. The actual development effort is only about 6 days + 23 days, because your productivity assumption is 25 pages/day; the majority of the elapsed timeline comes from the four testing stages and controlled code movements.

Yes. I would keep the main effort estimation without code merging, and show code merging/stage movement separately so there is no confusion.

1. Development & Testing Effort — Excluding Code Merge

| Activity | Phase 1 – 150 Pages | Phase 2 – 564 Pages |
| --- | --- | --- |
| Scope | Workflow & Checker pages | Reports & Misc. pages |
| Development productivity | 25 pages/day | 25 pages/day |
| Development effort | 6 days | 23 days |
| Testing productivity | 20 pages/day | 20 pages/day |
| Testing effort | 8 days | 29 days |
| QA buffer | 5 days | 5 days |
| Estimated Phase Duration | 13 working days | 34 working days |

Calculation:

- Phase 1: MAX(6 development days, 8 testing days) + 5 buffer = 13 days

- Phase 2: MAX(23 development days, 29 testing days) + 5 buffer = 34 days

Development and testing are assumed to run in parallel, since completed pages are released for testing on the same day.

2. Code Merging / Stage Movement — Separate Effort

Code merging is not included in the above 13-day / 34-day estimates.

| Stage Movement | Phase 1 | Phase 2 |
| --- | --- | --- |
| SIT → UAT | 3 days | 5 days |
| UAT → Staging | 3 days | 5 days |
| Staging → Pre-Prod | 3 days | 5 days |
| Total Code Merge / Movement Effort | 9 days | 15 days |

3. Overall Effort Including Code Merge

| Phase | Development & Testing | Code Merge / Stage Movement | Total Effort |
| --- | --- | --- | --- |
| Phase 1 – 150 pages | 13 days | 9 days | 22 working days |
| Phase 2 – 564 pages | 34 days | 15 days | 49 working days |
| Total – 714 pages | 47 days | 24 days | 71 working days |

Assumption to mention in the document

Code merging and stage movement are considered separately from the development and testing effort. For Phase 1, 3 working days are required for each stage movement (SIT → UAT, UAT → Staging and Staging → Pre-Prod), resulting in 9 working days. For Phase 2, 5 working days are required for each stage movement, resulting in 15 working days. These activities are not included in the development/testing duration and should be planned separately.